## Sheet1
Date | Activity | Date | Activity | Text Placement
2018-01-01 | Start of Project | 2018-01-01 | Start of Project | 20
2018-02-01 | Knowing Req. Of End Users | 2018-02-01 | Knowing Req. Of End Users | -20
2018-03-01 | Start Development Process | 2018-03-01 | Start Development Process | 20
2018-04-01 | Work on Interface, PM & make changes | 2018-04-01 | Work on Interface, PM & make changes | -20
2018-05-01 | Test & Run Project, Check & Correct Errors | 2018-05-01 | Test & Run Project, Check & Correct Errors | 20
2018-06-01 | End of Project | 2018-06-01 | End of Project | -20
Formulas:
Date = IF([Date]<>"",[Date],"")